## Time Table of Activities 2014
OBJECTIVE: The image of TVET in the Palestinian Territories is improved, and the visibility of TVET/LM services increased INDICATORS: 1. Regular media coverage, 2. Website traffic increased by 20%, 3. Newsletter subscribtions increased by 10%, 4. Regular updates/news on website, 4. Five students as ambassadors established
ACTIVITIES | TIMEFRAME | [10 empty] | RESPONSIBLE |  | REVIEW follow-up responsibility |  |  |  | AGREEMENTS | GIZ INPUT | Partner CONTRIBUTION | REMARKS
| 2014 | [10 empty] | GIZ | Partners | Month | Month | Month | Month
| Febr | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
| 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
TASK A - Digital Media
OUTPUT A1 - Active website with regular updates, increased traffic rates. Counterparts in ministries are feeling responsible regarding content
Up scaling website (cleaning up, structure, design) | [13 empty] | √
Defining content of Students/partners section | [14 empty] | x | x | √
Develop procedure manual
Training for partners/students | [16 empty] | x
OUTPUT A2 - Newsletter that informs partners and interested public on regular basis about news, activities etc. Content comes from partners. Subscriptions increased.
Newsletter format connected to website by web designer
Content restructuring
Defining/creating content of partners/students section
Define recipients list with partners
Develop procedure manual
Distribution of 1st TVET NL
OUTPUT A3 - Social Media (Facebook,youtube, twitter) gets interested youth involved and informed about TVET
Setting up of facebook page (in coop. wit partners, students)
Setting up of youtube channel
TASK B - Traditional Media
OUTPUT B1 - Media Coverage (print, national/international/ TV, radio, print)
Press releases (events/workshops/agreements)
Arranging interviews with partners for national media coverage
OUTPUT B2 - Interviews (TV/radio)
Interviews in radio/TV shows
Monthly TV/radio column
TASK C - Events
OUTPUT B1 - Open Days/TVET Knowledge Fair (schools, colleges, VTC's) → to attract general public - students/parents
Open Day with TVET institutions in Bethlehem/Hebron
Open Day with TVET institutions in Nablus
Organisation of Workshops (i.e. Quality assurance) with involvement of TVET students
OUTPUT B2 - Labour Market Information Events to promote services of OSS, LMIS, Career Units
Design and distribution of PR material
Strengthening network with private sector
OUTPUT C1 - National Events (Career Days/Week, Labour Day, summer camp)
Summer Camp
National Employment Week
OUTPUT C3 - Field visits for local media/journalists to ensure media coverage
Local radio/tv/print journalists visit TVET projects | [21 empty] | !
TASK D - Marketing/PR Material for TVET/LM institutions
OUTPUT D1 - Print Material (Fact sheet folder, brochures, leaflets)
Re-design fact sheet folder
Installment of TVET photos in inst.
Design of brochures, leaflets (VTC's) and distribution in schools
Brochures, leaflets, logo (CoC's). Distribution in schools in may | [16 empty] | x
TVET calendar 2015
OUTPUT D2 - Radio/TV spots/short image films for TVET institutions
Image film Quality assurance WS
TV/radio spots VTCs and colleges (EU)
TASK E - Media Training (PR counterparts/TVET institutions/students)
OUTPUT E1 - Media Training website/social media
Website training
social media training
media training
TASK F - Internal PR (GIZ colleagues are informed about TVET/LM activities and results)
OUTPUT F1 - Brown Bag Lunch
OUTPUT F1 - GIZ Intranet/Facebook
Legend:
|  |  | Current implementation | [9 empty] | Deliverable (e.g. Manual) |  |  | Project start
|  |  | Amended | [9 empty] | Workshop |  |  | Project end
|  | ! | Approval / decision required | [9 empty] | Training